## Instructions
Order, Operation & Machine Tracker — How to Use
PURPOSE
For every part, see exactly which operations are done, which are left, which machine each
needs, and how many days behind schedule it is — so anyone can pick this up if you're not there.
SHEETS
1. Parts Tracker — one row per PART, with 4 operation blocks (Laser Cutting / Bending / Welding / QC).
Leave an operation's Planned Date BLANK if that part doesn't need that operation at all.
2. Project Summary — rolls up each order: parts remaining, bottleneck part, days to dispatch.
3. Machine Load — shows queued parts per machine so you know where to send the next job.
HOW A PART ROW WORKS
- Fill Machine + Planned Date for every operation THIS part actually needs. Leave others blank.
- 'Remaining Operations' auto-lists whatever isn't marked done yet, e.g. 'Welding, QC'.
- 'Next Operation Due' + 'Days Behind' tell you the very next thing to chase, and by how many days
you're already late on it (0 = on schedule).
- 'Part Status' turns Red the moment any pending operation's planned date has passed.
DAILY ROUTINE
1. As each operation finishes, fill its Actual Completion date. That auto-updates everything else.
2. Check Machine Load first — send the next job to an Available machine, not an Overloaded one.
3. Check Project Summary — anything RED or ORANGE needs attention today.
4. The Bottleneck Part per project is the one furthest from finishing — chase that one first.
COLOR KEY
Blue text = cells you type into. Black text = formulas — do not overwrite.
Green = On Track / Available ¦ Orange = At Risk / Busy ¦ Red = Delayed / Overloaded
This sheet, the sample rows, and formulas can be edited freely — this is your working file.

## Parts Tracker
[5 empty] | Laser Cutting |  |  |  | Bending |  |  | Welding |  |  | QC
Order No | Project Name | Customer | Part No | Part Name | Machine | Sourcing Method | Planned Date | Actual Completion | Machine | Planned Date | Actual Completion | Machine | Planned Date | Actual Completion | Machine | Planned Date | Actual Completion | Final Planned Dispatch | Remaining Operations | Next Operation Due | Next Op Due Date | Days Behind | Part Status | Bottleneck Flag | _MatchKey | _DoneFlag
GDJ-2601 | Godrej Almirah Line | Godrej | P07 | Door Panel L | Laser-1 | In-House | 2026-09-10 | 2026-09-12 |  |  |  | Weld-3 | 2026-09-12 | 2026-09-14 | - | 2026-09-13 | 2026-09-15 | 2026-09-13 | ✅ All Done | ✅ All Done |  |  | ✅ Ready for Dispatch |  | Godrej Almirah Line | 1
GDJ-2601 | Godrej Almirah Line | Godrej | P08 | Door Panel R | Laser-1 | In-House | 2026-09-11 | 2026-09-11 |  |  |  | Weld-1 | 2026-09-14 | 2026-09-14 | - | 2026-09-15 | 2026-09-15 | 2026-09-15 | ✅ All Done | ✅ All Done |  |  | ✅ Ready for Dispatch |  | Godrej Almirah Line | 1
GDJ-2601 | Godrej Almirah Line | Godrej | P04 | Top Cover | Laser-2 | In-House | 2026-09-08 | 2026-09-09 | Bend-1 | 2026-09-12 | 2026-09-13 |  |  |  | - | 2026-09-13 | 2026-09-15 | 2026-09-13 | ✅ All Done | ✅ All Done |  |  | ✅ Ready for Dispatch |  | Godrej Almirah Line | 1
GDJ-2602 | Godrej Locker Batch | Godrej | P06 | Base Plate | Laser-2 | In-House | 2026-09-11 | 2026-09-12 | Bend-1 | 2026-09-14 |  |  |  |  | - | 2026-09-15 |  | 2026-09-15 | Bending, QC | Bending | 2026-09-14 | 12 | 🔴 Delayed |  | Godrej Locker Batch | 0
GDJ-2602 | Godrej Locker Batch | Godrej | P07 | Number Dial | Laser-1 | In-House | 2026-09-11 |  |  |  |  | Weld-2 | 2026-09-16 |  | - | 2026-09-18 |  | 2026-09-18 | Laser Cutting, Welding, QC | Laser Cutting | 2026-09-11 | 15 | 🔴 Delayed | ⚠ Bottleneck | Godrej Locker Batch¦BN | 0
JHN-2601 | Johnson Bracket Set | Johnson | P01 | Mount Bracket A | Laser-1 | In-House | 2026-09-09 | 2026-09-10 |  |  |  | Weld-4 | 2026-09-13 | 2026-09-13 | - | 2026-09-14 |  | 2026-09-14 | QC | QC | 2026-09-14 | 12 | 🔴 Delayed |  | Johnson Bracket Set | 0
JHN-2601 | Johnson Bracket Set | Johnson | P03 | Clamp Ring | Laser-2 | In-House | 2026-09-11 |  |  |  |  | Weld-4 | 2026-09-14 |  | - | 2026-09-15 |  | 2026-09-15 | Laser Cutting, Welding, QC | Laser Cutting | 2026-09-11 | 15 | 🔴 Delayed |  | Johnson Bracket Set | 0
JHN-2601 | Johnson Bracket Set | Johnson | P04 | Support Arm |  | In-House |  |  | Bend-1 | 2026-09-15 |  | Weld-5 | 2026-09-17 |  | - | 2026-09-18 |  | 2026-09-18 | Bending, Welding, QC | Bending | 2026-09-15 | 11 | 🔴 Delayed | ⚠ Bottleneck | Johnson Bracket Set¦BN | 0
WIN-2601 | Wheels India Rim Set | Wheels India | P01 | Rim Segment A | Laser-2 | In-House | 2026-09-09 | 2026-09-10 | Bend-1 | 2026-09-11 |  | Weld-6 | 2026-09-13 |  | - | 2026-09-14 |  | 2026-09-14 | Bending, Welding, QC | Bending | 2026-09-11 | 15 | 🔴 Delayed |  | Wheels India Rim Set | 0
WIN-2601 | Wheels India Rim Set | Wheels India | P04 | Spoke Bracket | Laser-1 | In-House | 2026-09-12 |  |  |  |  | Weld-6 | 2026-09-16 |  | - | 2026-09-17 |  | 2026-09-17 | Laser Cutting, Welding, QC | Laser Cutting | 2026-09-12 | 14 | 🔴 Delayed | ⚠ Bottleneck | Wheels India Rim Set¦BN | 0
SWT-2601 | Switch Panel Batch | Switch | P01 | Panel Frame |  | In-House | [5 empty] | Weld-7 | 2026-09-13 |  | - | 2026-09-14 |  | 2026-09-14 | Welding, QC | Welding | 2026-09-13 | 13 | 🔴 Delayed |  | Switch Panel Batch | 0
SWT-2601 | Switch Panel Batch | Switch | P03 | Mount Base |  | In-House | [5 empty] | Weld-8 | 2026-09-15 |  | - | 2026-09-16 |  | 2026-09-16 | Welding, QC | Welding | 2026-09-15 | 11 | 🔴 Delayed | ⚠ Bottleneck | Switch Panel Batch¦BN | 0
Formulas:
Final Planned Dispatch = MAX([Planned Date],[Planned Date],[Planned Date],[Planned Date])
Days Behind = IF([Next Operation Due]="✅ All Done","",IF(TODAY()>[Next Op Due Date],TODAY()-[Next Op Due Date],0))
Part Status = IF([Next Operation Due]="✅ All Done","✅ Ready for Dispatch",IF([Days Behind]>0,"🔴 Delayed",IF([Next Op Due Date]-TODAY()<=2,"🟠 At Risk","🟢 On Track")))

## Project Summary
Order No | Project Name | Customer | Promised Dispatch Date | Total Parts | Parts Completed | Parts Remaining | Bottleneck Part | Bottleneck Planned Date | Days to Dispatch | Project Status
GDJ-2601 | Godrej Almirah Line | Godrej | 2026-09-17 | 3 | 3 | 0 | - | - | -9 | ✅ Ready to Dispatch
GDJ-2602 | Godrej Locker Batch | Godrej | 2026-09-14 | 2 | 0 | 2 | Number Dial | 2026-09-18 | -12 | 🔴 Delayed
JHN-2601 | Johnson Bracket Set | Johnson | 2026-09-15 | 3 | 0 | 3 | Support Arm | 2026-09-18 | -11 | 🔴 Delayed
WIN-2601 | Wheels India Rim Set | Wheels India | 2026-09-16 | 2 | 0 | 2 | Spoke Bracket | 2026-09-17 | -10 | 🔴 Delayed
SWT-2601 | Switch Panel Batch | Switch | 2026-09-14 | 2 | 0 | 2 | Mount Base | 2026-09-16 | -12 | 🔴 Delayed
Bottleneck Part = the part with the latest 'Final Planned Dispatch' date among parts not yet fully done in that project.
Formulas:
Days to Dispatch = [Promised Dispatch Date]-TODAY()
Bottleneck Planned Date = IFERROR(INDEX('Parts Tracker'!$S3:S14,MATCH([Project Name]&"¦BN",'Parts Tracker'!$Z3:Z14,0)),"-")

## Machine Load
Machine | Station Type | Parts Queued (not completed) | Next Due Date | Load Status
Bend-1 | Bending | 3 | 2026-09-11 | 🔴 Overloaded
Laser-1 | Laser Cutting | 2 | 2026-09-11 | 🟠 Busy
Laser-2 | Laser Cutting | 1 | 2026-09-11 | 🟠 Busy
Weld-1 | Welding | 0 | - | 🟢 Available
Weld-2 | Welding | 1 | 2026-09-16 | 🟠 Busy
Weld-3 | Welding | 0 | - | 🟢 Available
Weld-4 | Welding | 1 | 2026-09-14 | 🟠 Busy
Weld-5 | Welding | 1 | 2026-09-17 | 🟠 Busy
Weld-6 | Welding | 2 | 2026-09-13 | 🟠 Busy
Weld-7 | Welding | 1 | 2026-09-13 | 🟠 Busy
Weld-8 | Welding | 1 | 2026-09-15 | 🟠 Busy
A machine can appear as the target for a part even if that part's turn hasn't arrived yet (earlier operations not done) — this counts every part currently assigned to it that isn't finished.
Formulas:
Next Due Date = IF([Parts Queued (not completed)]=0,"-",MINIFS('Parts Tracker'!$K3:K14,'Parts Tracker'!$J3:J14,[Machine],'Parts Tracker'!$L3:L14,""))
Next Due Date = IF([Parts Queued (not completed)]=0,"-",MINIFS('Parts Tracker'!$H3:H14,'Parts Tracker'!$F3:F14,[Machine],'Parts Tracker'!$I3:I14,""))